## Sheet1
Week of February 13
Team Member | Question | 2023-02-14 | 2023-02-16
Hyrum | What did you do since last scrum? | merged some pull requests | user authentication, README
| What are you doing until next scrum? | prototyping user authentication
| Is there anything blocking you? | max needs to set up tech stack
Shawn | What did you do since last scrum? | express prototype | worked on the readme, scrum backlog
| What are you doing until next scrum? | set up sprint planning documentation on jira, burndown
| Is there anything blocking you? | nope
Max | What did you do since last scrum? | set up tech stack for prototypes | .env files
| What are you doing until next scrum? | prototyping frontend | Helping everyone else set up their dotenv files
| Is there anything blocking you? | no | my own competence
Stockton | What did you do since last scrum? | express stuff | merged some pr's, express tutorial
| What are you doing until next scrum? | activity diagram, express tutorial | Want to become familiar with figma; finish swimlane stuff
| Is there anything blocking you? | nope | not this time
Braden | What did you do since last scrum? | added my express tutorial to get and figured out how to create a pull request | express tutorial
| What are you doing until next scrum? | continuing express tutorial
| Is there anything blocking you? | nope
Week of February 20
Team Member | Question | 2023-02-21 | 2023-02-23
Hyrum | What did you do since last scrum? | lint, yarn, mock components for login view, add redirect to root route | manage vehicles UI
| What are you doing until next scrum? | manage vehicles UI
| Is there anything blocking you? | nope | no
Shawn | What did you do since last scrum? | planning documents | reviewing and merging pull requests
What are you doing until next scrum?
| Is there anything blocking you? | no | nah
Max | What did you do since last scrum? | login endpoints | finished updating the user model and permissions
| What are you doing until next scrum? | Configure database | Making github more useable for everyone
| Is there anything blocking you? | No | No
Stockton | What did you do since last scrum? | swimlanes, set up database | Became familiar with what we have on figma
| What are you doing until next scrum? | Going to start work on manage reservations view | Implementing our figma in VScode for manage reservations view
| Is there anything blocking you? | Not really | shouldn't be
Braden | What did you do since last scrum? | reviewing and testing the codebase
What are you doing until next scrum?
Is there anything blocking you?
Week of February 27
Team Member | Question | 2023-02-28
Hyrum | What did you do since last scrum? | add delete handler
What are you doing until next scrum?
Is there anything blocking you?
Shawn | What did you do since last scrum? | midterms
| What are you doing until next scrum? | imdterms
| Is there anything blocking you? | midterms
Max | What did you do since last scrum? | Finished some user endpoints
| What are you doing until next scrum? | Getting married
| Is there anything blocking you? | getting super married
Stockton | What did you do since last scrum? | Manage reservations view
| What are you doing until next scrum? | Manage reservations view
| Is there anything blocking you? | gotta study for the compilers midterm
Braden | What did you do since last scrum?
What are you doing until next scrum?
Is there anything blocking you?
Week of March 13
Team Member | Question | 2023-03-14 | 2023-03-16
Hyrum | What did you do since last scrum? | added create modal to manage vehicles view, restructured vehicle object | finished the manage users page
| What are you doing until next scrum? | manage users page | delete vehicle functionality
| Is there anything blocking you? | Differential geometry is taking priority | Still bogged down with differential geometry
Shawn | What did you do since last scrum? | test existing backend endpoints | continued testing
| What are you doing until next scrum? | building front end ui | learn Vcard and vue datepicker
Is there anything blocking you?
Max | What did you do since last scrum?
What are you doing until next scrum?
Is there anything blocking you?
Stockton | What did you do since last scrum? | Not much; spring break was busy | Made progress on manage reservations view, using user view as a template
| What are you doing until next scrum? | Make more progress on manage reservations | Finish manage reservations view
| Is there anything blocking you? | should be good for now | midterm coming soon-ish
Braden | What did you do since last scrum? | not a thing
| What are you doing until next scrum? | hopefully something
| Is there anything blocking you? | grandma died, colonoscopy
Week of March 20
Team Member | Question | 2023-03-21 | 2023-03-23
Hyrum | What did you do since last scrum? | added images to vehicle endpoints | delete vehicle functionality
| What are you doing until next scrum? | functionality for deleting a vehicle | prepare repo for submission
| Is there anything blocking you? | nope | nah
Shawn | What did you do since last scrum? | Started browse view | made some progress on the browse view
| What are you doing until next scrum? | work on the browse view | keep working on browse view
| Is there anything blocking you? | nah | got a date during next meeting
Max | What did you do since last scrum? | Connected User Login View | Connected user management view
| What are you doing until next scrum? | Some more user endpoints for the user management view | Making some reservation endpoints
| Is there anything blocking you? | no | Homework
Stockton | What did you do since last scrum? | Not much | Finished ui for manage reservations
| What are you doing until next scrum? | going to finish the manage reservations ui | Pick up new frontend task; planning on doing the reservations tab
| Is there anything blocking you? | big linear algebra midterm is this week | taking linear algebra midterm on Saturday
Braden | What did you do since last scrum? | scrum documents
| What are you doing until next scrum? | testing some endpoints
| Is there anything blocking you? | no
Week of March 27
Team Member | Question | 2023-03-28 | 2023-03-29
Hyrum | What did you do since last scrum? | last-minute fixes for the submission
| What are you doing until next scrum? | preparing the submission
Is there anything blocking you?
Shawn | What did you do since last scrum? | worked on browse view | finish browse view
| What are you doing until next scrum? | going to finish the browse view | finish testing browse view
Is there anything blocking you?
Max | What did you do since last scrum? | Finished some more vehicle info endpoints
| What are you doing until next scrum? | Finishing some reservation endpoints
| Is there anything blocking you? | Homework
Stockton | What did you do since last scrum? | Made progress on reservations tab ui | Reservations tab ui is done
| What are you doing until next scrum? | ui for the reservations tab | Help prepare everything for milestone submission
| Is there anything blocking you? | nope, we're good | nope
Braden | What did you do since last scrum?
What are you doing until next scrum?
Is there anything blocking you?